## Sheet1
Elements | Responsibility | Status/Comments | Timelines
Immediate Requirements:
Website Content:
Slider and offer page to be created | Narayan & Tushar |  | Monday, 5 November 2012, 1st half | Elements
Ping product list & images | Kevin, Kirat & Tushar | Flash file to be procured | WIP |  | High Priority
New product list & images | Kevin, Kirat & Tushar |  | WIP |  | Medium Priority
Proofreading of Product descriptions | Kirat |  | WIP |  | Low Priority
Product videos | Kevin, Kirat & Tushar |  | WIP
Displaying bags in different colors in the Customise it! section according to user's selection | Narayan & Tushar | Not Possible [ Flash is reuiqred ] | TBD
Feedback/Corrections:
Customise it! page | Narayan | Edit button to be added, Error msg to appear on selecting the same position more than once, Error msg to appear on not selecting Yes and uploading a file/entering any detail | WIP
Check required fields in registration form | Tushar | Error message to be edited | 2012-11-05
Colour of font in dropdown boxes from Wishlist & Cart to be checked | Narayan & Tushar | Wishlist to be used as reference | 2012-11-05
Invoice process to be changed | Narayan & Tushar | Filename of the PDF to be changed to golfessentials.in Invoice_(invoice no.) | WIP
Print order summary option (through PDF) | Narayan & Tushar |  | TBD
Placement of page nos. on products pages | Narayan | 4 rows of products to appear on each page with page number below | TBD
Hover over image to zoom' to be added on product pages. Alternative views to be added |  |  | TBD
Free Shipping to be changed to Free Delivery |  |  | TBD
Your activity section in My Account | Narayan & Tushar | Comments & ratings | TBD
Quick look' button |  |  | TBD
Search box; Change copy for search results, Order of elements (Corrections w.r.t. Product Categories (Feedback sent on 15.10.12) | Kirat, Narayan & Tushar |  | TBD
Sign in box on rollover | Narayan & Tushar |  | TBD
This will be a gift' button |  |  | TBD
Placement of feedback & special order buttons |  |  | TBD
Placement of Men's, Ladies etc…special offers tab |  |  | TBD
Buy later option | Narayan & Tushar |  | TBD
Reloading of page after submitting a review | Narayan & Tushar |  | TBD
Go to top' button |  |  | TBD
Social Media:
Like us on Facebook & Follow us on Pinterest buttons | Narayan |  | 2012-11-05
Signatures | Narayan & Tushar | FB URL to be added (www.facebook.com/golfessentials.in), Pinterest page to be linked (www.pinterest.com/golfessentials) | 2012-11-05
Creation of Twitter, Instagram & Wikipedia page | Kevin & Kirat |  | TBD
Communication:
Emails - On registering, On receiving a special order, On receiving feedback, On receiving a message through contact us, On placing an Order, Customise it! orderConfirmation of availability + invoice, On dispatching products, Items in your wishlist for over 2 months, Forgot your password, Email confirmation : Change of password/email/personal info, Unsubscribe, Share by mail | Narayan | Refer Feedback PPT; Ensure that the emails go out only once | WIP
Collation of contacts etc. | Kevin, Kirat & Tushar |  | 2012-11-05
Promotional mailer | Narayan |  | WIP
Emailers to be sent | Kevin, Kirat & Narayan |  | 2012-11-06
SMSes to be sent | Kevin & Kirat |  | 2012-11-06
Designing of offer newsletter | Kevin, Kirat, Tushar & Narayan |  | 2012-11-07
Google ads | Kevin & Kirat |  | 2012-11-07
Gift certificates | Narayan & Tushar |  | TBD
Gift boxes | Kevin, Kirat & Tushar |  | TBD
Promotional material:
Golf balls with the logo | Kevin |  | Done
Designing of car stickers | Kevin, Kirat & Narayan |  | TBD
Others:
Daily analytics to be sent across | Tushar |  | WIP
SEO | Kevin, Kirat & Jaswant |  | WIP
Mobile site | Kevin, Kirat, Tushar & Narayan |  | TBD
Logo guidelines | Kirat |  | TBD
Long-term Requirements:
Payment Gateway Integration | Kevin & Tushar |  | TBD
SSL Certificate | Narayan & Tushar |  | TBD
Live chat | Narayan & Tushar |  | TBD
What other customers are looking at right now | Narayan & Tushar |  | TBD
Total number of members (tab above FB & Twitter tabs) | Narayan & Tushar |  | TBD
Security (Refer internethobbies.com) | Kevin, Kirat, Narayan & Tushar |  | TBD
Weekend/Beginning of the week sale | Kevin, Kirat, Narayan & Tushar |  | TBD