## Sheet1
Elements | Responsibility | Status/Comments | Timelines
Immediate Requirements:
Website Content:
New product list & images | Kevin, Kirat & Tushar |  | WIP
Proofreading of Product descriptions | Kirat |  | WIP | Elements
Product videos | Kevin, Kirat & Tushar |  | WIP |  | High Priority
Displaying bags in different colors in the Customise it! section according to user's selection | Narayan & Tushar |  | TBD |  | Medium Priority
Low Priority
Feedback/Corrections:
Check required fields in registration form | Tushar | Refer feedback PPT | 2012-10-30
Shipping address on checkout page to appear blank | Narayan & Tushar |  | 2012-10-30
Functionality of dropdown boxes from Wishlist & Cart to be checked | Narayan & Tushar |  | 2012-10-30
Customise it! page WIP | Narayan | Edit button to be added, Error msg to appear on selecting the same position more than once, Error msg to appear on not selecting Yes and uploading a file/entering any detail | 2012-10-30
Check product description of Taylormade Visor | Tushar | Refer feedback PPT | 2012-10-30
"Please select the option of your choice to add the product to your cart or wishlist" on product pages to be in bold | Narayan & Tushar | Refer feedback PPT: Please select the option of your choice to add the product to your cart or wishlist | 2012-10-30
Product descriptions on all product pages to be left aligned | Tushar |  | 2012-10-30
Payment options to be left aligned | Tushar |  | 2012-10-30
Check pricing of products when searched through search box | Tushar | Refer Kevin's mail | 2012-10-30
Print order summary option (through PDF) | Narayan & Tushar |  | 2012-10-31
Placement of page nos. on products pages | Narayan | 4 rows of products to appear on each page with page number below | 2012-10-31
Redirection on registering to homepage | Narayan & Tushar |  | 2012-10-31
Messages on submission on various requests appearing on the page | Kirat | Proofreading | WIP
Invoice process to be changed | Narayan & Tushar | Filename of the PDF to be changed to golfessentials.in Invoice_(invoice no.) | WIP
Search box; Change copy for search results, Order of elements (Corrections w.r.t. Product Categories (Feedback sent on 15.10.12) | Kirat, Narayan & Tushar |  | TBD
Sign in box on rollover | Narayan & Tushar |  | TBD
Buy later option | Narayan & Tushar |  | TBD
Reloading of page after submitting a review | Narayan & Tushar |  | TBD
Social Media:
Share this product: Email | Narayan | Email copy to be added: Refer Feedback PPT | 2012-10-30
Share this product: Email | Narayan | Share by email to work without logging in | Tuesday 30 October 12 - Wednesday 31 October 12
Share this product: Pinterest | Narayan | Settings of Pin it button to be edited such that the description appears automatically | 2012-11-01
Like us on Facebook & Follow us on Pinterest buttons | Narayan |  | 2012-11-01
Signatures | Narayan & Tushar | FB URL to be added (www.facebook.com/golfessentials.in), Pinterest page to be linked (www.pinterest.com/golfessentials) | 2012-11-01
Creation of Twitter, Instagram & Wikipedia page | Kevin & Kirat |  | TBD
Communication:
FB invites | Kevin, Kirat, Tushar & Narayan |  | WIP
Emails - On registering, On receiving a special order, On receiving feedback, On receiving a message through contact us, On placing an Order, Customise it! orderConfirmation of availability + invoice, On dispatching products, Items in your wishlist for over 2 months, Forgot your password, Email confirmation : Change of password/email/personal info, Unsubscribe, Share by mail | Narayan | Refer Feedback PPT; Ensure that the emails go out only once | 2012-10-30
Promotional mailer | Narayan |  | 2012-10-31
Emailers to be sent | Kevin, Kirat & Narayan |  | Thursday 01 November 12 - Friday 02 November 12
SMSes to be sent | Kevin & Kirat |  | 2012-11-02
Collation of contacts etc. | Kevin, Kirat & Tushar |  | WIP
Designing of offer newsletter | Kevin, Kirat, Tushar & Narayan |  | 2012-11-05
Google ads | Kevin & Kirat |  | 2012-11-05
Gift certificates | Narayan & Tushar |  | TBD
Gift boxes | Kevin, Kirat & Tushar |  | TBD
Promotional material:
Golf balls with the logo | Kevin |  | Done
Designing of car stickers | Kevin, Kirat & Narayan |  | TBD
Others:
Daily analytics to be sent across | Tushar |  | WIP
SEO | Kevin, Kirat & Jaswant |  | WIP
Mobile site | Kevin, Kirat, Tushar & Narayan |  | TBD
Logo guidelines | Kirat |  | TBD
Long-term Requirements:
Payment Gateway Integration | Kevin & Tushar |  | TBD
SSL Certificate | Narayan & Tushar |  | TBD
Live chat | Narayan & Tushar |  | TBD
What other customers are looking at right now | Narayan & Tushar |  | TBD
Total number of members (tab above FB & Twitter tabs) | Narayan & Tushar |  | TBD
Security (Refer internethobbies.com) | Kevin, Kirat, Narayan & Tushar |  | TBD
Weekend/Beginning of the week sale | Kevin, Kirat, Narayan & Tushar |  | TBD