## Sheet1
Elements | Responsibility | Status/Comments | Timelines
Immediate Requirements:
Website Content:
Sliders & Banners | Kevin & Tushar | Purchase of slider/Improvement to be looked into | Wednesday 24 October 12 - Thursday 25 October 12
Proofreading of Product descriptions | Kirat |  | WIP | Elements
Product videos | Kevin, Kirat & Tushar |  | WIP |  | High Priority
Displaying bags in different colors in the Customise it section according to user's selection | Narayan & Tushar |  | TBD |  | Medium Priority
Low Priority
Feedback/Corrections:
Updating preferred contact options | Narayan & Tushar |  | 2012-10-25
Check required fields in registration form | Tushar | Birthday to be changed to Age (age groups to be added (Below 18, 18-30, 30-50, Above 50) | 2012-10-25
Placement of page nos. on products pages | Narayan | 4 rows of products to appear on each page with page number below | 2012-10-25
Shipping address on checkout page to appear blank | Narayan & Tushar |  | 2012-10-25
Print order summary option (through PDF) | Narayan & Tushar |  | 2012-10-25
Check alignment of Invoices table in My account | Narayan & Tushar | There is no invoice table now. | 2012-10-25
Product descriptions on all product pages to be left aligned | Narayan |  | 2012-10-25
Messages on submission on various requests appearing on the page | Kirat | Proofreading | Thursday 25 October 12 - Friday 26 October
Redirection on registering to homepage | Narayan & Tushar |  | TBD
Invoice process to be changed | Narayan & Tushar | Filename of the PDF to be changed to golfessentials.in Invoice_(invoice no.) | TBD
Customise it! page |  | Edit button to be added, Error msg to appear on selecting the same position more than once, Error msg to appear on not selecting Yes and uploading a file/entering any detail | TBD
Search box; Change copy for search results, Order of elements (Corrections w.r.t. Product Categories (Feedback sent on 15.10.12) | Kirat, Narayan & Tushar |  | TBD
Sign in box on rollover | Narayan & Tushar |  | TBD
Buy later option | Narayan & Tushar |  | TBD
Reloading of page after submitting a review | Narayan & Tushar |  | TBD
Social Media:
Share this product: Email, Facebook, Twitter, Pinterest | Narayan | WIP: Email copy to be added, Settings of Pin it button to be edited such that the description appears automatically, Share by email to work without logging in | Thursday 25 October 12 - Friday 26 October
Like us on Facebook & Follow us on Pinterest buttons | Narayan |  | 2012-10-23
Signatures | Narayan & Tushar | golfessentials.in logo to be linked to the website, FB URL to be added (www.facebook.com/golfessentials.in), Pinterest page to be linked (www.pinterest.com/golfessentials) | 2012-10-23
Creation of Twitter & Wikipedia page | Kevin & Kirat |  | TBD
Communication:
FB invites | Kevin, Kirat, Tushar & Narayan | WIP | Wednesday 24 October 12 - Thursday 25 October 12
Emails - On registering, On receiving a special order, On receiving feedback, On placing an Order, Confirmation of availability + invoice, Items in your wishlist for over 2 months, Forgot your password, Email confirmation : Change of password/email/personal info, Unsubscribe, Share by mail | Narayan | Refer Feedback PPT | Thursday 25 October 12 - Saturday 27 October 12
SMSes to be sent | Kevin & Kirat |  | TBD
Emailers to be sent | Kevin, Kirat & Narayan |  | TBD
Collation of contacts etc. | Kevin, Kirat & Tushar |  | WIP
Designing of offer newsletter | Kevin, Kirat, Tushar & Narayan |  | TBD
Google ads
Gift certificates (to be made available before the festive season): email (fridgedoor) | Narayan & Tushar |  | TBD
Gift boxes (to be made available before the festive season) | Kevin, Kirat & Tushar |  | TBD
Promotional material:
Golf balls with the logo | Kevin |  | Done
Designing of car stickers | Kevin, Kirat & Narayan |  | TBD
Others:
Daily analytics to be sent across | Tushar |  | Thursday 25 October 12 - Friday 26 October 12
SEO | Kevin, Kirat & Jaswant |  | 2012-11-01
Mobile site | Kevin, Kirat, Tushar & Narayan |  | TBD
Logo guidelines | Kirat |  | TBD
Long-term Requirements:
Payment Gateway Integration | Kevin & Tushar |  | TBD
SSL Certificate | Narayan & Tushar |  | TBD
Live chat | Narayan & Tushar |  | TBD
What other customers are looking at right now | Narayan & Tushar |  | TBD
Total number of members (tab above FB & Twitter tabs) | Narayan & Tushar |  | TBD
Security (Refer internethobbies.com) | Kevin, Kirat, Narayan & Tushar |  | TBD
Weekend/Beginning of the week sale | Kevin, Kirat, Narayan & Tushar |  | TBD