## Sheet1
Elements | Responsibility | Status/Comments | Timelines
Immediate Requirements:
Website Content:
New product list & images | Kevin, Kirat, Tushar & VKU | Golf Studio images + Cleveland, Srixon, Cobra etc. | WIP | High Priority
Proofreading of Product descriptions | Kirat |  | WIP | Medium Priority
Ping product list & images | Kevin & Tushar | Clarifications to be sought on putters | WIP | Low Priority
Ping flash file to be procured | Kevin | Awaiting file from Ping | 2012-11-16
Product videos | Kevin, Kirat & Tushar |  | WIP
Displaying bags in different colors in the Customise it! section according to user's selection | Narayan & Tushar |  | TBD
Feedback/Corrections:
Customise it! page | Narayan | Error message on position conflict to be changed, Sign in/Register in steps, No. of embroderies, Mailer on price on request | Done, feedback to be incorporated
Invoice process to be changed | Narayan & Tushar | Filename of the PDF to be changed to golfessentials.in Invoice_(invoice no.), Address & Tin no. to be edited. | WIP
Banner to be edited | Narayan | Offer banner at the bottom of the page to be recreated | Friday 16 November - Saturday 17 November 2012
Brand logos to appear differently |  |  | TBD
Print order summary option (through PDF) | Tushar |  | TBD
Percentage count for page load (on customise it!) | Narayan | Could be a golf ball being formed | TBD
HTML converter for Product Descriptions |  |  | TBD
Buy later option | Narayan |  | TBD
Hover over image to zoom' to be added on product pages. Alternative views to be added |  |  | TBD
Free Shipping to be changed to Free Delivery |  |  | TBD
Your activity section in My Account | Narayan | Comments & ratings | TBD
Placement of feedback & special order buttons |  |  | TBD
Placement of Men's, Ladies etc. |  |  | TBD
Search box; Change copy for search results, Order of elements (Corrections w.r.t. Product Categories (Feedback sent on 15.10.12) | Kirat, Narayan & Tushar |  | TBD
Sign in box on rollover | Narayan & Tushar |  | TBD
Quick look' button |  |  | TBD
This will be a gift' button |  |  | TBD
Reloading of page after submitting a review | Narayan & Tushar |  | TBD
Go to top' button |  |  | TBD
Social Media:
Signatures | Narayan & Tushar | Follow us and stay updated Facebook - www.facebook.com/golfessentials.in Twitter - www.twitter.com/golf_essentials Pinterest - www.pinterest.com/golfessentials Instagram - www.instagram.com/golfessentials | Friday 16 November - Saturday 17 November 2012
Follow us/Like us buttons | Narayan | Buttons to be added: Facebook, Twitter, Pinterest, Instagram. Refer http://www.hautelook.com/events#all | Friday 16 November - Saturday 17 November 2012
Creation of Wikipedia page | Kevin & Kirat |  | TBD
Communication:
Emails - On registering, On receiving a special order, On receiving feedback, On receiving a message through contact us, On placing an Order, Customise it! orderConfirmation of availability + invoice, On dispatching products, Items in your wishlist for over 2 months, Forgot your password, Email confirmation : Change of password/email/personal info, Unsubscribe, Share by mail | Narayan | Refer Feedback PPT; Check formatting on gmail etc. as well | WIP
Collation of contacts etc. | Kevin, Kirat & Tushar | Done: CGC Mobile & Email IDs, PGC Mobile, Enssner Emails | WIP
Google ads | Kevin & Kirat |  | TBD
Promotional mailer to be finalised | Narayan | Buttons to be added: Facebook, Twitter, Pinterest, Instagram | Week of 12 November 12
Emailers to be sent | Kevin, Kirat & Narayan |  | TBD
SMSes to be sent | Kevin & Kirat |  | TBD
Designing of offer newsletter | Kevin, Kirat, Tushar & Narayan |  | Week of 19 November 12
Gift certificates | Narayan & Tushar |  | TBD
Gift boxes | Kevin, Kirat & Tushar |  | TBD
Promotional/Packaging material:
Golf balls with the logo | Kevin |  | Done
Tape for packing with the golfessentials.in logo | Kevin & Kirat |  | TBD
Designing of car stickers | Kevin, Kirat & Narayan |  | TBD
Others:
SEO | Kevin, Kirat & Jaswant |  | TBD
Mobile site | Kevin, Kirat, Tushar & Narayan |  | TBD
Logo guidelines | Kirat |  | TBD
Long-term Requirements:
Payment Gateway Integration | Kevin & Tushar |  | TBD
SSL Certificate | Narayan & Tushar |  | TBD
Live chat | Narayan & Tushar |  | TBD
What other customers are looking at right now | Narayan & Tushar |  | TBD
Total number of members (tab above FB & Twitter tabs) | Narayan & Tushar |  | TBD
Security (Refer internethobbies.com) | Kevin, Kirat, Narayan & Tushar |  | TBD
Weekend/Beginning of the week sale | Kevin, Kirat, Narayan & Tushar |  | TBD